## Sheet1
CSCI822 – Systems Development
Meeting Minutes
Date: | 2016-03-09 | Venue: | UOW Library GS6
Start: | 5:30pm | Chair:
End: | 8:pm | Minutes: | Boycy Carreon
Attendees: | Boycy | Apologies: | Praveen
Syed
Tam
Muhammad
TOPICS
No. | Topic | No. | Subtopic | Responsible | Duration | Outcomes
1 | Assignment of roles |  |  | Tam | 10 mins. | There will be a rotation of logistics and project roles. Assignment of roles will be assigned based on the agreed tasks.
2 | Planning Activities |  |  | Muhammad | 20 mins.
|  | 2.1 | Tasks Scheduling and Assignment |  |  | Trello will be our scheduling tool
|  | 2.2 | Source Control |  |  | GIT will be our source control platform. Meeting minutes will be stored here.
|  | 2.3 | Team Communication |  |  | Slack will be our team communication platform. Slack has been setup.
|  | 2.4 | Urgent team messages |  |  | WhatsApp will be our immediate team communicator
3 | Business Case |  |  | Syed | 30 mins
|  | 3.1 | What is this system that you are to build? |  |  | QA System for UOW Students
|  | 3.2 | Who will it serve? |  |  | UOW Students
|  | 3.3 | What will it do for them? |  |  | A. Any information UOW-related B. Anonymosity C. Enable quick integration to the Uni culture
4 | Questions to ask client |  |  | Tam |  | Tam compiles the questions
5 | Features/User |  |  | Muhammad | 30 mins
|  | 5.1 | Non-functional requirements |  |  | A. High availability – 97.1 B. Maintenance
|  | 5.2 | Functional Requirements (Features) |  |  | Defined the subsystems: A. User Managerment B. Question C. Search
6 | User Management Subsystem | 6.1 | Registration |  |  | Only possible with a valid UOW email account
|  | 6.2 | Profile |  |  | A. Photograph/Avatar
B. Reputation
C. Activity- Questions Answered/Asked – nice to have
D. Interests (tags) – nice to have
E. Phone Numbers – nice to have
|  | 6.3 | Users |  |  | Blocking User – for discussion with the client
7 | Question Subsystem |  |  |  | 20 mins.
|  | 7.1 | Posting a NEW question |  |  | A. Tags B. Show community guidelines to user. C. Title and Body
|  | 7.2 | Unanswered Question |  |  | Can be filtered by: A. Time B. Ranking C. Tags
|  | 7.3 | Interesting Question |  |  | * Order of answers to be determined * Can be filtered by: A. Time B. Ranking C. Tags
8 | Search Subsytem |  |  |  |  | A. Filtering based on tags B. Use some open source library, then questions will be indexed for the database.
ACTION ITEMS
No. | Item | Responsible | Deadline | Comments
1 | Create team accounts for Slack, GIT, Trello, WhatsApp | Tam | Before Bext Week | Almost Done
2 | How to order answers/replies | Muhammad | Next week